## How to use
ERP Data Migration Checklist
Digital Adaption · digitaladaption.co.uk · free to use within your business
What this is
24 tasks across six phases, sequenced the way real migrations actually have to run. Each phase gates the next; skipping trial loads is how go-lives fail quietly.
How to use it
Assign an owner and due date to every task. Anything Blocked gets escalated at the weekly data meeting, not discovered at cutover.
Example rows
Rows marked EXAMPLE show how a completed entry should look. Overwrite or delete them.
Need help?
Digital Adaption is an independent ERP and data consultancy on the Wirral. If this surfaces problems you want help fixing: digitaladaption.co.uk/contact

## Checklist
ERP Data Migration Checklist
The full task list from scoping to post go-live, in loading-sequence-aware order.
Progress: | 0 of 24 tasks complete
Phase | Task | Owner | Depends on | Status | Due | Evidence / notes
1. Scope & strategy | Inventory every source system, owner and extract route
1. Scope & strategy | Define what is migrating vs archiving vs rebuilding, per domain
1. Scope & strategy | Agree data ownership matrix with named business owners
1. Scope & strategy | Set reconciliation control totals and tolerances with finance
2. Audit & cleansing | Profile master data: duplicates, completeness, validity rates
2. Audit & cleansing | Publish data quality baseline and weekly burn-down
2. Audit & cleansing | Cleanse in source or staging, never during the load
2. Audit & cleansing | Resolve unit-of-measure and costing-method conflicts across sites
3. Mapping & build | Complete field-level source-to-target mapping with transform rules
3. Mapping & build | Define load sequence respecting referential integrity
3. Mapping & build | Build repeatable load scripts/tooling with error logging
3. Mapping & build | Catalogue business-critical reports for continuity rebuild
4. Trial loads | Trial load 1: full volume, log every error, fix at source
4. Trial loads | Trial load 2: target <2% rejects, reconcile control totals
4. Trial loads | Rebuild critical reports against trial-load data and validate
4. Trial loads | User validation: business owners check their own domains
5. Rehearsal & cutover | Dress rehearsal: full cutover runbook executed against the clock
5. Rehearsal & cutover | Freeze master data changes in legacy; exceptions logged
5. Rehearsal & cutover | Cutover weekend: load, reconcile, finance sign-off, go/no-go
5. Rehearsal & cutover | Rollback plan tested and authority to invoke agreed
6. Post go-live | Hypercare: daily data triage with owners for first 2-4 weeks
6. Post go-live | Reconcile every business-critical report against legacy
6. Post go-live | Hand quality rules into BAU governance with review cadence
6. Post go-live | Lessons learned logged while they still hurt