## How to use
ERP Data Migration Project Planner
Digital Adaption · digitaladaption.co.uk · free to use within your business
What this is
A 30-week migration plan with a live Gantt chart, pre-loaded with the phases and durations of a realistic mid-sized ERP data migration. Dates are formulas: change the start date and everything shifts.
How to use it
Set your project start date (blue cell, Plan tab). Adjust task start/end dates to your reality - the bars redraw automatically. Use it alongside the ERP Data Migration Checklist; phases match.
Need help?
Digital Adaption is an independent ERP and data consultancy on the Wirral. If this surfaces problems you want help fixing: digitaladaption.co.uk/contact

## Plan
ERP Data Migration Project Planner
Change the project start date in the blue cell and the whole plan, dates and chart, moves with it.
Project start (Mon): | 2026-07-06
[8 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30
ID | Phase | Task | Owner | Start | End | Days | Status | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25
1 | 1. Scope & strategy | Source system inventory & extract routes |  | 2026-07-06 | 2026-07-17 | 12
2 | 1. Scope & strategy | Data ownership matrix agreed |  | 2026-07-13 | 2026-07-24 | 12
3 | 1. Scope & strategy | Migration scope decisions per domain |  | 2026-07-13 | 2026-07-31 | 19
4 | 1. Scope & strategy | Control totals & tolerances agreed with finance |  | 2026-07-20 | 2026-07-31 | 12
5 | 2. Audit & cleansing | Data profiling & quality baseline |  | 2026-07-20 | 2026-08-14 | 26
6 | 2. Audit & cleansing | Cleansing burn-down (source/staging) |  | 2026-08-03 | 2026-10-09 | 68
7 | 3. Mapping & build | Source-to-target field mapping |  | 2026-08-03 | 2026-09-11 | 40
8 | 3. Mapping & build | Load tooling build & error logging |  | 2026-08-24 | 2026-09-25 | 33
9 | 3. Mapping & build | Business-critical report catalogue |  | 2026-08-10 | 2026-09-04 | 26
10 | 4. Trial loads | Trial load 1 (full volume) |  | 2026-09-28 | 2026-10-09 | 12
11 | 4. Trial loads | Fix cycle 1 - errors to source |  | 2026-10-05 | 2026-10-23 | 19
12 | 4. Trial loads | Trial load 2 (target <2% rejects) |  | 2026-10-26 | 2026-11-06 | 12
13 | 4. Trial loads | Report rebuild & validation on trial data |  | 2026-10-12 | 2026-11-13 | 33
14 | 4. Trial loads | Business owner data validation |  | 2026-11-02 | 2026-11-20 | 19
15 | 5. Rehearsal & cutover | Cutover dress rehearsal (timed) |  | 2026-11-23 | 2026-12-04 | 12
16 | 5. Rehearsal & cutover | Legacy master data freeze |  | 2026-12-07 | 2026-12-18 | 12
17 | 5. Rehearsal & cutover | Cutover weekend: load, reconcile, sign-off |  | 2026-12-14 | 2026-12-18 | 5
18 | 6. Post go-live | Hypercare (see Hypercare Playbook) |  | 2026-12-21 | 2027-01-15 | 26
19 | 6. Post go-live | Report reconciliation vs legacy |  | 2026-12-21 | 2027-01-08 | 19
20 | 6. Post go-live | First month-end close & BAU handover |  | 2027-01-11 | 2027-01-29 | 19