## How to use
Post Go-Live Reporting Reconciliation Checklist
Digital Adaption · digitaladaption.co.uk · free to use within your business
What this is
A register of every business-critical report with its legacy counterpart, reconciliation method and sign-off. This is how you stop the 'nobody trusts the numbers' phase after go-live.
How to use it
Catalogue reports BEFORE cutover. Reconcile each new report against the final legacy extract. Nothing gets used for decisions until its status says Reconciled.
Example rows
Rows marked EXAMPLE show how a completed entry should look. Overwrite or delete them.
Need help?
Digital Adaption is an independent ERP and data consultancy on the Wirral. If this surfaces problems you want help fixing: digitaladaption.co.uk/contact

## Reconciliation
Post Go-Live Reporting Reconciliation Checklist
Every business-critical report, reconciled against legacy before anyone is allowed to trust it.
Report name | Business area | Legacy source | New source | Owner | Reconciliation method | Tolerance | Legacy value | New value | Variance | Status | Signed off by | Date
Stock valuation by warehouse (EXAMPLE) | Finance | Legacy ERP GL | Power BI / LN | FD | Line-by-line vs final legacy extract | ±£500 | 1245300 | 1244880 | -420 | Reconciled | J. Smith | 2026-06-01
Open order book (EXAMPLE) | Sales | Legacy report S-04 | LN session + report | Sales Dir | Order count and value totals | Exact | 876450 | 876450 | 0 | Reconciled | A. Jones | 2026-06-02